## SPRINT0
ESTIMATED COST OF THE PROJECT (BAC) |  |  |  | BAC | 10168
IoT components
Component | Cost | Platform | Observations
ESP32 | 15 | Amazon | 2 units
AHT25 | 5 | Amazon | 3 units
Capacitive Sensor | 12 | Amazon | 3 units
BH1750 | 11 | Amazon | 3 units
TOTAL | 43
Working hours budget
Member | € / hour | Calculation | Total cost
Marc | 15 | 3 × 3 × 15 | 2025
Ainhoa | 15 | 3 × 3 × 15 | 2025
Flavià | 15 | 3 × 3 × 15 | 2025
Giuseppe | 15 | 3 × 3 × 15 | 2025
Cinta | 15 | 3 × 3 × 15 | 2025
TOTAL |  |  | 10125

## SPRINT1
COST CONTROL - SPRINT 1
Main cost values
BAC | 10168 | PV | 2295 | AC | 2317.5 | EV | 2295 | PV - AC | -22.5
Tasks
Task | EH | Member | FH | Progress | PV (€) | AC (€) | EV (€)
Adding BBDD features | 2 | flaviaserret04 & Tigre44 | 4 | 100% | 30 | 60 | 30
BBDD Restructuration | 5 | Tigre44 | 13 | 100% | 75 | 195 | 75
Cost evaluation of the Project on Sprint 1 | 15 | marcc28 | 10 | 100% | 225 | 150 | 225
DevOps Automation Workflows | 4.5 | flaviaserret04 | 4.5 | 100% | 67.5 | 67.5 | 67.5
Display Weather Forecast in the App | 14 | atnic15 | 18 | 100% | 210 | 270 | 210
Fields Features | 9.5 | ainhoaaf | 6.5 | 100% | 142.5 | 97.5 | 142.5
Final Documentation | 5 | flaviaserret04 & Tigre44 & ainhoaaf & marcc28 & atnic15 | 5 | 100% | 75 | 75 | 75
Implement APP Dashboard | 18 | ainhoaaf | 13.5 | 100% | 270 | 202.5 | 270
Implement APP Feed | 14 | flaviaserret04 | 14 | 100% | 210 | 210 | 210
Implement APP Profile | 15 | ainhoaaf | 14 | 100% | 225 | 210 | 225
Implement Login System | 12 | flaviaserret04 | 12 | 100% | 180 | 180 | 180
Implement Multilanguage on APP | 4 | flaviaserret04 | 4 | 100% | 60 | 60 | 60
Implement SignUp System | 13 | flaviaserret04 | 13 | 100% | 195 | 195 | 195
MockUp Figma | 15 | marcc28 | 16 | 100% | 225 | 240 | 225
Risk Analysis | 7 | marcc28 | 7 | 100% | 105 | 105 | 105
TOTAL SPRINT 1 | 153 |  | 154.5 |  | 2295 | 2317.5 | 2295
Performance
Metric | Calculation | Value | Interpretation
CPI | EV / AC | 0.99029 | Cost overrun
SPI | EV / PV | 1 | On or ahead of plan
CV | EV - AC | -22.5 | Unfavourable
SV | EV - PV | 0 | Favourable
Forecast
Metric | Calculation | Value | Meaning
EAC | BAC / CPI | 10267.6863 | Estimated total cost
ETC | EAC - AC | 7950.1863 | Estimated remaining cost
VAC | BAC - EAC | -99.6863 | Expected budget variance

## SPRINT2
COST CONTROL - SPRINT 2
Main cost values
BAC | 10168 | PV | 285 | AC | 330 | EV | 95 | PV - AC | -45
Tasks
Task | EH | Member | FH | Progress | PV (€) | AC (€) | EV (€)
Implement Arduino/ESP32 IoT Sensor Node | 19 | Tigre44 & marcc28 | 22 | 33.33% | 285 | 330 | 95
Weather alerts for the current garden | 0 | atnic15 | 0 | 0% | 0 | 0 | 0
TOTAL SPRINT 2 | 19 |  | 22 |  | 285 | 330 | 95
Performance
Metric | Calculation | Value | Interpretation
CPI | EV / AC | 0.28788 | Cost overrun
SPI | EV / PV | 0.33333 | Behind plan
CV | EV - AC | -235 | Unfavourable
SV | EV - PV | -190 | Unfavourable
Forecast
Metric | Calculation | Value | Meaning
EAC | BAC / CPI | 35320.4211 | Estimated total cost
ETC | EAC - AC | 34990.4211 | Estimated remaining cost
VAC | BAC - EAC | -25152.4211 | Expected budget variance